## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: | KANO
Reporting period: |  | FY 2024
SABER Focal Person: |  | IMAM INUWA GWALE
List of contributing entities: |  |  | State Government and Private Sectors
URL Link to the published BERAP |  |  | Finance.kn.gov.ng. | land.kn.gov.ng | https://knupda.kn.gov.ng/
Is this plan approved by the State Executive Council (SEC) |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  |  | 27th December 2023

## KANO BERAP
¦
KANO STATE BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) FOR 2024
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Estimated costs | Planned Start Date | Planned End Date
1 | Access to Information | To provide adequate policies and reforms that would provide transperency in governments procedures, access to information, clear cut processess to encourage new businesses. | 1. Our plan is to leverage on digital platforms (Web Portals, Document Management Portals) that would provide quick access to information. 2. Policies and Reforms shall be created in collaboration with supporting MDA's to ensure transperency in processess and procedural activities and importantly to publish such reforms and information | 1. New Businesses can now have direct access to information quickly with out bottlenecks 2. Time reduction in access to information and the ability to understand what is required to setup a business without having to know anyone | Business Communities | KanInvest | Ministry of Justice, Min. of Finance, Public Procurement Bureau. Bureau of Land, KNUPDA,Min of Planning and Budget,Min of Science and Tech,Min of Information | 70000000 | 2024-01-01 | 2024-12-01
2 | Enhanced Regulatory Reforms | To reduce the bottlenecks and durations for applicable regulations in setting up a business | Make available all regulatory procedures for easy access through our digital platforms | This will provide transperency and reduce the time for getting necessry regulatary documents | Business Communities | KanInvest | Ministry of Commerce,Investment, Industry,Cooperatives, and Solid Mineral, Ministry of Justice, Min of Land and Physical Planning, KNUPDA,KIRS. | 50000000 | 2024-01-01 | 2024-06-01
3 | Update of Web link to relevant MDAs website for ease of access | This will update linkages with relevant MDAs website and ease access to vital information. Thus facilitating the one-stop-shop for investors. | 1. Finalization of Update of Website by relevant MDAs (Bureau for Land, KNUPDA, Commerce, KIRS). 2. Creation of direct website Link on the KanInvest Website to the MDAs | Update of Website by the MDAs in line with the Business Enabling Reform areas. Acquisition of source code for access and creation of the link on the KanInvest Website. | Investors and the general public | KanInvest | Ministry of Land and Physical Planning, KNUPDA, KIRS, Ministry of Commerce,Min of Science and Tech | 70000000 | 2024-03-01 | 2024-04-01
4 | Update documentation of all investment incentives in Kano | To provide all information on incentives available for investors from both the State and Federal Government | 1. Compilation of all investment incentives available in the State. 2. Compilation of all investment incentives offered by the Federal Government. 3. Integration of the incentives into one package. | 1. Collation of all incentives available in the State. 2. Collation of all incentives for investors both local and foreign offered by the Federal Government. 3. Harmonization of the incentives into one document, digitalization of same and uploading to the KanInvest website for ease of access. | Potential investors | KanInvest | Ministry of Land and Physical Planning, KNUPDA, KIRS, Ministry of Commerce, Min. of Justice, Agriculture, Health, Environment, Nigeria Custom Service, Nigeria Immigration Service, NEPC, NIPC, CAC, FIRS, NEPZ | 30000000 | 2024-06-01 | 2024-08-01
5 | Update of Investor Checklist on the KanInvest Website | To update checklist for investors to obtain information of all prerequisites for investing in the State. | 1. Integration of the investor checklist with relevant laws and policies of government. 2. Share the updated checklist with Relevant stakeholder MDAs. 3. Submission of Checklist to KanInvest Management committee for validation. 4. Uploading of the updated checklist on the KanInvest Website | 1. Engagement with stakeholder MDAs for integration of relevant policies and laws 2. Work with consultants to Harmonize the checklist based on best practices. 3. Submit the finalized checklist to higher authority for final validation. 4. Uploading of a downloadable checklist to the KanInvest website. | Investors, KIRS | KanInvest | Ministry of Land and Physical Planning, KNUPDA, KIRS, Ministry of Commerce, Min. of Justice, Agriculture, Health, Environment, Nigeria Custom Service, Nigeria Immigration Service, NEPC, NIPC, CAC, FIRS, NEPZ | 100000000 | 2024-03-01 | 2024-07-01
6 | Public-Private-Partnership Law | Enactment of a PPP Law to establish standards and nodalities for PPP models of investment in the State. | 1. Draft PPP bill drawn up and incorporating the relevant PPP modalities to be adopted 2. Bill sent to the Ministry of Justice for legal review/legal drafting. 3. Bill presented to the EXCO for validation or amendment. 4. Bill sent to the House of Assembly for scrutiny and enactment | 1. Drafting of a PPP document for the State by KanInvest. 2. Submission of the draft Bill to Min. of Justice for legal review. 3. Presentation to State Executive Council on the PPP Law by KanInvest. 4.Forwarding of the Approved PPP Bill to Kano State House of Assembly. 5.Follow up by KanInvest with the KSHA. | Investors, busineesses, development partners, organizations, KIRS and Public Procurement Bureau | KanInvest | Ministry of Justice, House of Assembly, Min. of Finance, Public Procurement Bureau. | 100000000 | 2024-01-01 | 2024-04-01
7 | One-Stop-Shop | To establish connectivity between relevant government agencies, by providing efficient, transparent and fast tracked services to investors. | 1. Provision of ICT infrastructure. 2. Set up of the connectivity. 3. Creation and integration of an e-businees platform linking all relevant MDAs. 4. Train relevant service providers from the various MDAs 5. Monitor and evaluate. | 1.Creation of a single window platform where investors can apply for business registration, submit relevant documents, and make appropriate fee payments. 2. Enable KanInvest to be able to track and review the services of participating agencies at the centre. 3.To provide investment facilitation services and reduce the time required to process regulatory approvals and permits through integration. | Ministry Commerce, KIRS, Bureau of land management , Investors, general public. | KanInvest | Ministry of Land and Physical Bureau for Land Management, KNUPDA, KIRS, Ministry of Commerce,Investment, Industry, Cooporative and Solid Minerals. Min. of Justice,Judiciary, Agriculture, Health, Environment,Ministry of Science and Tech, etc., | 30000000 | 2024-04-01 | 2024-11-01
8 | GIS based Automation processes of obtaining C of O and post C of O processes | Enhancement of Revenue Collection, Facilitate C of O processes, Online access to official maps survey plans, Cadastral plans digitization, assessment, e-payment by the general public, and Transparency | 1. Enhancement of revenue collection 1.1. conversion of analog based data to digital geodatabase (e.g conversion of Analog Survey plans to digital), used in automated billing system, e.g land used charge, CofO processing, post CofO processing (ongoing with 20,000 units scanned land files and related land records) 2. Facilitate C of O process 2.1 Skills enhancement and sharing, for sustainability for service delivery 3. Online access to official Maps, assessment, and Land title status by general public 3.1 enhancement of official website for online assessment/billing, payment, maps, information and techincal services 3.2 Online customer care 4. Transparency 4.1. Adequate Records management, proper audit and accuracy D.2 Facilitate building plan approval. | Draft Bill to be passed by State Assembly The key target is to sustain GIS based automation processes online | Government, Civil Servants (Min of Land and Physical Planning, KNUPDA) and General Public. | Min of Land and Physical Planning | KNUPDA, Fire Service, ministry of Justice, Police Service Commision, Housing Cooperation, Local Government, Emirate Council, Ministry Of Commerce,NMDPRA, KANINVEST,KIRS | 45000000 | 2024-01-01 | 2024-12-01
9 | E-court service portal | 1. Facilitate State acess to justice 2. Enables Access to e-forms,fIling and procedures for easy retrieval. | 1. Creation of e-court platform 2. Sourcing of the technical personnel 3. Training and onboarding of Users 4. Digitalization of Court data for easy access | 1. To facilitate access to e-court services online. 2. To enable quick resolution of cases through digitalization of court data and procedures. | General Public. | High Court | 1- Sharia Courts, 2-Ministry of Justice | 50000000 | 2024-01-01 | 2024-12-01
10 | Consolidation and Codification of State & Local Government revenue administration Law | The aim of the reform is to review the consolidated State & Local Government revenue laws, and to ease the payment of these revenues | 1. To allow for raising single demand notice to tax payers and single collecting MDA 2. To update single and unified payment solution 3. Approval for the joint state & local government revenue committee. | To harmonise all Taxes/levies in order to have a single Demand Notice. | Taxpayers | KIRS. | State House of Assembly, Min. of Finance, Min. of Justice, Min. for Local Government,Min of Land and Physical Planning | 5000000 | 2024-01-01 | 2024-12-01
11 | Strenghtening Taxpayers Grieviance and Complaint Redress Mechanism (Tax Clinic) | To strengthen enabling enviroment for communication with State teaming taxpayers where taxpayers can diectly lay complaints and be address in good time, it’s a unit that educates the taxpayers on the importance of paying taxes as and when due. | To inculcate into our teaming taxpayers a voluntarily tax compliance habit, which most of the taxpayers are currently lacking. | Sensitization through organising Tax dialoques, Seminars, Conferences, Radio jingles, meetings with traditinal Rulers and religious Leaders. | 1. Government is the major beneficiary of the project because voluntary tax compliance will lead to a significant increase in the State IGR which will allow the government to finance its laudable programs and projects. 2. Taxpayers will also benefit from services provided by the government | Kano State Internal Revenue Service (KIRS) | Ministry of Information and Ministry for Local Government and Chieftancy affairs | 5000000 | 2024-01-01 | 2024-12-01
12 | Automation process | To ease taxpayers sufferings and blocking of revenues leakages by automating the entire tax process including the : Tax payer profiling, assessment,collection, accounting and reporting. | 1. Bringing our products and services to taxpayers door-step through Tax process automation. 2. 2. To integrate KIRMAS into KIGRA as payment gateway | Total movement from paper work to digital, and the key targets are; taxpoayers, tax administrators and practisioners. | The Government would have a comprehensive taxpayers database for manupulations and future recurrences | KIRS/Lead Technical advisers Messr. ITC System Global Nigeria. Supervised by Min. of Finance. | Office of the Head of service Kano State | 5000000 | 2024-06-01 | 2026-06-30
13 | Online business premises registration | To fast track business premises registration and reduce the process within 24 hours after payment | 1. Training of staff for quick response and effective monitoring on the platform. | 1. Access to e-registration form for online filling and submission by applicants. 2. Online printout of notification of payment and access to e-Certification for printing. | Businnesses, General Public, Government | Min. of Commerce | KIIRS, KAnInvest, Bureau of Statistices, SERVICOM. | 30000000 | 2024-01-01 | 2024-12-01
14 | Construction of 108Km Fibre Optic Network in Metropolitan Kano - | 1. To unify fibre infrastructure by the deployment of a single cable duct for all telecommunication companies operating in the State, improving internet access to Government institutions and businesses, enhancing E-Governance, and exploring other revenue sources (internet access for organizations etc). | 1. Ducting & Sub-ducting infrastructure services 2. Fibre cable installation | Integrating ICT and other communication line into underground single duct | Government Offices, Businesses | Ministry of Works and Infrastructure | KNUPDA, Fire Service, ministry of Justice, Police Service Commision, Housing Cooperation, Local Government, Emirate Council, Ministry Of Commerce, DPR, KANINVESTKNUPDA, | Construction of 78Km Fibre Optics Network N1, 991,599,761.29 Construction of 30Km Fibre Optics Network N 764, 768, 658. 27 | 2024-04-01 | 2024-12-01
15 | Provision of efficient, reliable and affordable electricity that is environmentally friendly (Construction of Tiga & Challawa Hydro-Power Project) | 1. Provision of reliable and affordable electricity to light industries 2. Improve business activities in the state through provision of uninterupted power supply to the major segment of businesses thereby reducing militating power instability | 1. Construction of Generating Station : Challawa is ongoing 2. Evacuation of electricity power 3. Set up of a Transmission sub-station 4. Completion of a Distribution station 5. Completion of Distribution lines | 1. availability of clean energy (environmentally friendly) 2. Improving electricity supply for commercial/industrial areas 3. improving water supply to industrial areas. | Industry, businesses and general public | Min. of Works and Infrastructural Development | KHEDCO | Kano Hydro power project N1,088,938,272.31 | January, 2014 | 2024-12-01
16 | e - government in the state | 1. To ensure transparency in state government activities 2. To simplify the process | Ensure utilisation of the State Integrated Financial Management Information System (SIFMIS) | Automation of all Government financial transaction of the state | Public financial management MDAs | Ministry of Finance SIFMIS | 1. Ministry of Finance 2. Ministry of Planning and Budget, 3. Office of the head of civil service, 4. Audit office(State and Local Govt), 5. Public procurement bureau 6. Kano Internal Revenue Service | 50000000 | 2024-01-01 | 2024-12-01
17 | Policy Review/ Developemt | To review and develop some policies and bills that will improve service delivery in line with the state development priorities | Institutionalizing state development plan prioritiies across 11 sectors of the state | Review of the existing Medium Term Sector Strategy (MTSS) of 9 sectors and remaining 2 are ongoing in the state | All MDAs | Min of Planining & Budget | Ministry of Works and Infrastructure, Education, health, Agric,Commerce, Justice,information,Women affairs,Environment, Local government OHCS | 100000000 | 2024-03-01 | 2024-08-01

## Progress Report (hidden)
BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
| The focus area for the reforms eg transparency of official fees and procedures | What the State intends to achieve by implementing the Business Enabling Reform | Very detailed, step by step process on how the objective will be achieved | Explain actions and/or sub-actions and include targets | One MDA responsible for the action/activity | Supporting MDAs | Estimated budget for the action/activity | When you commit to start the implementation of the actions | When you commit to complete the actions and achieve your targets | Indicate whether the action/activity is completed, ongoing - on time, ongoing - delayed or dropped | Describe the status of each action, explaining reasons for any delays or actions being dropped. Explain any changes that occurred during implementation affecting start and end dates | Describe next steps for the outstanding actions. For example, is the action getting carried over to the following year's action plan?
1 | Illustrative example: Transparency of official fees and procedures | Illustrative example: This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs | Illustrative example A. Finalise process mapping of one business regulatory area number 1 | A description of the action and target, e.g. business regulatory process mapping signed off by all included MDAs and approved by the relevant authority | List the one MDA that would be responsible for this action/activity | List the several MDAs that would actively contribute to the activity | Amount (in Naira) | Day, Month, Year | Day, Month, Year
Illustrative example A.1. Map existing process for carrying out impact evaluation
B.
B.1
B.2
C.
C.1
C.2